## Slide 1: Colorado Health Benefits Exchange
Board Meeting
January 23, 2011

## Slide 2: Overview
Drafts of both the Technology and Service RFP and the Program Management Office RFP have been released and reviewed by staff, consultants, partners and the COHBE Board
Both RFPs are ready for release 1/23/2012
Process to evaluate and select vendors will be presented to Exchange board for review and approval

## Slide 3: Process to evaluate Service and Tech Platform Vendor
COHBE ACQUISITION SCHEDULE This schedule may change as needed.
EVENT |  | DATE/End of Day Mountain Time
1. | COHBE Releases RFP | January 23, 2012
2. | Pre-Bid Vendor Conference | January 31, 2012 10:00 am Mountain Time
3. | Deadline for Submitting Written Questions Requesting Clarifications | February 3, 2012
4. | Deadline for COHBE to Post Final Responses to Written Questions | February 10, 2012
5. | Proposal Submission Deadline (RFP Closing Date) | February 27, 2012
6. | Notification of Vendors Selected for Software Demonstrations, Orals and/or Discovery | March 9, 2012
7. | Product Demonstrations, Orals and Discovery Sessions | March 19 to March 23, 2012
8. | COHBE Issues a Call for Best and Final Offers (BAFOs) | March 26, 2012
9. | Deadline for Vendor BAFO Responses | April 2, 2012
10. | COHBE Conducts Evaluation of BAFOs | April 2 to April 9, 2012
11. | Evaluation Committee Recommendation to the COHBE Board | April 9, 2012
12. | Vendor(s) Notified of Selection(s) | April 9, 2012
13. | Begin Contract Negotiations w/ Selected Vendor(s) including drafting SOW(s) | April 11 to May 4, 2012
14. | Evaluation Team provide recommendation to Board for Award | Board Meeting
15. | Award / Contract Signed | May 4, 2012 (after Board Meeting)
16. | Detailed Project Plan and Project Kick-off | May 10, 2012

## Slide 4: Process to evaluate Program Management Office
COHBE ACQUISITION SCHEDULE This schedule may change as needed.
EVENT |  | DATE/End of Day Mountain Time
1. | COHBE Releases RFP | January 23, 2012
2. | Deadline for Submitting Written Questions Requesting Clarifications | January 27, 2012
3. | Deadline for COHBE to Post Final Responses to Written Questions | January 31, 2012
4. | Pre-Bid Vendor Conference | February 6, 2012
5. | Proposal Submission Deadline (RFP Closing Date) | February 10, 2012
6. | Review and select top 3 proposals | February 13, 2012
7. | Orals Presentations | February 21 - 22, 2012
8. | Vendor Selection | February 24, 2012
9. | Contract Negotiation | February 24 – March 1, 2012
10. | Evaluation Team provide recommendation to Board for Award | February 27, 2012
11. | Initial Contract Period (Phase 1) Option for 18 month renewal | March 5 – September1, 2012